## Needs Identification
GUIDE TO RTHE CONSULT FEEDBACK ON SPECIFIC REQUIREMENTS!
[7 empty] | Existing or will be done | > | Project Scope - these two domains will form the scope of the project as we see it.
Existing but to be tweaked, doable - to be worked on, and/or to be explored
[7 empty] | Future project or not doable | > | This domain represents what may form future upgrades, OR what WARP-D cannot do due to complexities avoidance to protect the whole system and ensure best performance.
| JP Trustees - WARP-D FMS Project | Needs Identification
| Required Modules or Variations | Guiding Remarks | Specific requirements - Client Inputs | Project Design & Actions Points | Table design required | Picture attach | RTHE Feedback on Specific Requirements |  | Requirements/Dependencies to do the work | Template received? (Y/N)
1 | Updated ordering module | Ordering shall factor duties and levies, and include a column for additives costing | 1. Set up petroleum taxes, NPA Levies and Bost Margin | David to find the UI, if not we develop a new UI for this. |  |  | Already exists |  | Latest duties & levies schedule |  | Jeffrey to share Restocking template
|  |  | 2. Owner cost and additive cost | 1) Create additive cost line in margin analysis 2) Do this primarily in additive module |  |  | Doable - to be included |  | Full additive analysis schedule
|  |  | 3. Order planning and stocking analysis section | Okay |  |  | Already exists - no changes will be made to the existing modules
|  |  | 4. The system should allow the upload of pre-populated data | Okay |  |  | Already exists - pilot test checks to confirm
|  |  | 5. Enter loading particulars into the system | Okay |  |  | Already exists - pilot test checks to confirm
|  |  | 6. Assign same loaded consignment to multiple stations | Okay |  |  | Already exists - pilot test checks to confirm
|  |  | 7. Real time loading report to show loadings completed from the loading plan. | Okay |  |  | Already exists - pilot test checks to confirm. Note this is subject to real time inputs by relevant staff
|  |  | 8. Increase the number tanks per product for all stations up to 5 | Okay |  |  | Already exists - tank setup is done to suit needs and there are no limitations
|  |  | 9. UPPF table for transporters - Orders through BRVs | Create BRV UI - where transporters, their trucks can be entered for drop down usage during ordering. Link to product loading under order mgmt & station order mgmt |  |  | Already exists - tank setup is done to suit needs and there are no limitations |  | Updated NPA UPPF schedule & all BRVs in the system
|  |  | 10. Inter tank and inter station product transfers | N/A |  |  | Not to be done
2 | Discharge module | Discharge of products at the station | 1. The system should allow for Station Managers to input details of pre-discharge procedures of products received at their station for approval in the system ahead of their discharges. | Design the window, link to temp variance analysis module per pictures taken |  |  | Doable - to be included |  | Existing template |  | A basic window that is 1) per station 2) Final discharge quantity inclusive - link from discharge window 3) Extract report - enabled
|  |  | 2. The system should allow SMs to upload pictures of their delivery notes, dipsticks before and after discharge. |  |  |  | Already exists - pilot test checks to confirm
|  |  | 3. The system should be able to display a discharge report showing the discharge details required and the overages or shortages | Rename the shortage analysis or temp variance modules |  |  | Doable - to be included |  | Existing template
3 | Updated margin analysis report | Report shall factor duties and levies, and include a column for additives costing |  | Find the template and update it to have a UI as applicable |  |  | Doable - to be included |  | Existing template
4 | Additives analysis module | Module shall include all costing for additive; it shall act like price change, where additive price changes or doping ratio shall not affect previous transactions; the module shall feed into the Update Ordering Module & Margin analysis | 1.Track movement of additive between Central warehouse and depots. It should generate reports | DUPLICATE STATION ORDER MGMT MODULE & ADAPT PER PICTURE ----- Treat as an order 1) Central warehouse setup as a BDC, 2) Depots set up as stations to receive 3) Depots like stations to have stock balances and additive Kg consumed 4) Calculate theoretical stock consumed using doping ratio 5) Run variance of 3 & 4 |  |  | Doable - to be included |  |  |  | Treat as an order 1) Central warehouse setup as a BDC, 2) Depots set up as stations to receive 3) Depots like stations to have stock balances and additive Kg consumed 4) Calculate theoretical stock consumed using doping ratio 5) Run variance of 3 & 4
|  |  | 2.The module should be able to update ones doping ratios are entered during product ordering | Design per picture - use system generated fuel cost thinking for margin analysis. Link Additive module to margin analysis module |  |  | Doable - to be included |  | Existing template
|  |  | 3.JP doping ratios should be pre populated in the system | Design per picture - use system generated fuel cost thinking for margin analysis. Link Additive module to margin analysis module |  |  | Doable - to be included |  | Existing template
5 | Stock variance module | Module shall display stock variances recorded on a daily basis | The system should be able to calculate the stock variances per station on a daily basis and generate a report | Okay |  |  | Already exists - pilot test checks to confirm
6 | Temperature variation module | Shall capture the loaded qty, discharged qty, and expected discharge qty per temp variation and run stock variation analysis. | The system should be able to compute the expected stocks to be received for each discharge based on the temperature at the time of the discharge and based on that compute the compensated volume variations. | Design the temp variance analysis module per pictures taken |  |  | Doable - to be included |  | Existing template
7 | Pictures upload functionality in modules | Extend current functionality across board - make it viewable where doable. | 1.System should allow pictures,vidoes,pdf,xls,csv etc files 2.System shoud allow export of follwing file types excel,csv,kaban |  |  |  | Already exists - pilot test checks to confirm. No provision for video uploads.
8 | Sales variance module | Add required columns eg price, NCTs, etc to run variance calculations |  |  |  |  | Doable - to be included |  | Existing template
9 | NCT Module | Develop module to capture summary of all Non-Cash Transaction types (MoMo, POS, JuniPay, etc) - link to DSRB | 1. System should be able to track all pending NCTs with their status confirmation role assigned to Risk team. 2. Confirmed pending NCTS should update pre- stated amounts and update vaiances. | Design per template provided using the credit summary - the module should run cumulative variance per picture taken & linked to cash & credit summary dashboard |  |  | Module is doable
10 | API Integration | Define ERPNext integration capabilities & align WARP-D | 1.Integration should allow relevant data to be mapped to ERPNext. Data transfer should be direct and seemless. NO upload on account data from FMS to ERPNext | Last stage of project |  |  | NOT CLEAR! Irrespective, API integration will be a mini project handled with ERPNext and JP Trustees.
11 | Credit Module | For creating credit customers and credit limits, approving credit sales and tracking credit customers' balances | 1.Creation of credit and prepayment customers should be permitted for Risk team | Identify UI location and show at the front end |  |  | Already exists - pilot test checks |  | Credit limits and days per customer
|  |  | 2.Retail Manager and TMs should have permission to approve credit sale requests | Okay BUT Finance approved. |  |  | Already exists - systems is designed for Finance approve credit sales with Marketing inputs
|  |  | 3.Permission should be given to view credit balances of customers. | Develop the OMC credit module per picture taken, using BDC version. |  |  | Finance module is doable - timeline may vary
|  |  | 4. Creation on Coupon based for some Credit Customers. | Template based |  |  | doable - standalone window |  |  |  | A standalone window - focus is efficiency and rapid reporting
12 | Expense Module | For creating expenses for approval by TMs | SMs should be able to request station expenses on the system and attach relevant pictures for TM's approval | Genset expenses tracking in the Cash & Credit summary & link to NCTs module |  |  | doable - for genset expenses tracking & link to NCTs |  |  |  | For genset expenses tracking & link to NCTs
13 | Goods-In-Transit Report | Explore developing a module that tracks loaded products so as to give a GIT report for trucks that have not been discharged. | Provide at any point in time the products yet to be discharged with their respective details | Use variation of the UPPF module with 2 additional columns - 1st column inputs from station order mgmt, and 2nd column with "if" function - Discharged or GIT. |  |  | GIT module is doable - timeline may vary |  | All truck data
14 | Sales Module |  | 1 Compute the cost of product when sale is triggered | Edit margin analysis |  |  | Captured under margin analysis
|  |  | 2. SMs should be able to enter sales details for each shift including but not limited to Meter readings (both electronic and manual), RTTs and NCTs | okay. |  |  | Already exists
|  |  | 3.Compute sales volume per price change | okay. |  |  | Already exists
|  |  | 4 Graphical representation of daily and monthly sales volumes per station and per product for all stations at a glance | okay. |  |  | Already exists - reporting module should cater for this
|  |  | 5. SMs should be able to upload pictures of their meter readings | Add picture functionality across board |  |  | feature exists and will be extended
|  |  | 6. SMs should be able to enter their cash banked per day's sales. | okay |  |  | doable
|  |  | 7. Undergroung tank analysis based on the day's sales | okay |  |  | Already exists
|  |  | 8. The system should generate a cash variance report per day and per month and per station. | Design per pencil schematic |  |  | doable |  | Existing template
|  |  | 9. Closing meter numbers should be picked automatically from the system | okay |  |  | doable
|  |  | 10. Cost of the PMS,AGO and Additive should be computed in a separate report once | Margin analysis |  |  | Explain!
|  |  | 11. The system should populate loyalty points of Customers. |  |  |  | Not doable
|  |  | 12. Fuel Delivery Section |  |  |  | Not doable
15 | Performance Monitoring Module |  | 1. Retail Manager should be able to set sales targets for stations. 2. Station performance per target should be displayed on the system. 3. The system should allow sales performance for various stations to be compared. 4. Retail Manager should be able to set incentive targets on the system. 5. A report on stations performance with respect to incentive targets should be available on the system. |  |  |  | doable - standalone window |  |  |  | 1) Window should capture daily targets for SMs 2) Pull meter readings from pump sales (auto) 3) Calculate variance 4) Colour variance - traffic light
16 | Validation Module |  | 1. BRA team should have a dashboard for validating all NCTs and cash banked on the system. 2. The system should generate a report on the totals of the unvalidated NCTs and cash reported. 3. The system should be able to generate variances between the expected cash per sales recorded and the validated amounts. | As above |  |  | Doable
17 | System Setup |  | 1. Creations of individual/new stations factoring details such as COCO, CODO, DODO, DOCO tank capacity as well as whether the station is a Shell station or a JP 2. Setup staff with their roles/permissions 3. Setup transporters and trucks in the system 4. System should have colour coding for various statuses | Setup issue |  |  | System setup will be upgraded to capture most concerns BUT possibly not all e.g. colour coding across board. |  | All data to be setup
18 | Other System Packages
|  |  | 1. Automated e-mail notifications | Designed |  |  | WARP-D has its own messaging & notification system; this will be used and connection to emails will be considered later
|  |  | 2. Different Access levels | Setup issue |  |  | Already exists - to be setup
|  |  | 3. Activity logs and audit trails | Okay |  |  | Already exists
|  |  | 4. Images and videos on work report per month 300GB | Okay |  |  | Storage is available but beyond a level, at a cost
|  |  | 5. Storage available per month 250 GB | Okay |  |  | Storage is available but beyond a level, at a cost
|  |  | 6. Notifications per month 15,000 | Okay |  |  | Already exists - notifications will be unlimited
|  |  | 7. Data backup and backup log | David to document the DR plan for communication to JP. |  |  | Will be worked on - nevertheless all data shall be in the cloud on a secure server
19 | Lubricant Module |  | 1. Lubes ordering section |  |  |  | Future module - N/A now.
|  |  | 2. Lubes distribution section |  |  |  | Future module - N/A now.
|  |  | 3. Lubes reporting section | Update the section with their own lubricants |  |  | Already exists |  | Current lubes (names, pack sizes, etc.)
|  |  | 4. Lubes accounting section |  |  |  | Future module - N/A now.
|  |  | 5. Lubes validations section |  |  |  | Future module - N/A now.
[7 empty] | Existing or will be done | > | Project Scope - these two domains will form the scope of the project as we see it.
Existing but to be tweaked, doable - to be worked on, and/or to be explored
[7 empty] | Future project or not doable | > | This domain represents what may form future upgrades, OR what WARP-D cannot do due to complexities avoidance to protect the whole system and ensure best performance.

## Next Steps
Project Steps Outlook | Timelines | RtHE Team | JP Team
Sign NDA | Immediate
Agree on the project scope | May 17th, 2023
Develop, agree and sign off SOW - including payment terms | May 25th, 2023
Execute project | Per SOW
Pilot stations | Per SOW
Upgrade per pilot outcomes | Within 2 - 3 weeks of pilot
Team training | Per SOW
Full roll-out | Per SOW
Responsible
Not responsible